# Agile Ceremonies — Sprint 1

Real-Time Order Tracking Enhancement — Food Delivery Application

This document captures the Agile/Scrum ceremonies conducted for Sprint 1: Backlog Refinement, Sprint Planning, Daily Stand-up, Sprint Review, and Sprint Retrospective, along with the Business Analyst's contribution to each.

# 1. Backlog Refinement

Backlog refinement is the process of reviewing and preparing user stories before they are selected for a sprint. During refinement, the Business Analyst and Agile team reviewed requirements, clarified acceptance criteria, identified dependencies, assessed complexity, and ensured stories were sufficiently clear and actionable for development.

| Story | Priority | Points | Dependency | Ready for Sprint? |
| --- | --- | --- | --- | --- |
| US-01 — View Current Order Status | High | 5 | None | Yes |
| US-02 — Food Preparation Status | High | 3 | US-01 | Yes |
| US-03 — Delivery Partner Assignment | High | 3 | US-01 | Yes |
| US-04 — Live Delivery Tracking | High | 8 | US-03 | Yes |
| US-05 — ETA Display | High | 5 | US-04 | Yes |
| US-06 — Order Status Notifications | Medium | 3 | US-01 | Yes |

Dependency Analysis

The user stories were reviewed for functional dependencies. Basic order status functionality is required before more advanced tracking capabilities can be implemented. Delivery partner assignment is required before live delivery tracking can begin, while ETA functionality depends on delivery progress information. These dependencies were considered during Sprint Planning to ensure stories were delivered in a logical sequence.

# 2. Sprint Planning

| Item | Details |
| --- | --- |
| Sprint | Sprint 1 |
| Duration | 2 weeks |
| Sprint Goal | Enable customers to view and understand their order progress from order placement through delivery. |
| Planned Capacity | 14 Story Points |
| Total Product Backlog | 27 Story Points |

Sprint Backlog

| User Story | Points |
| --- | --- |
| US-01 — View Current Order Status | 5 |
| US-02 — Food Preparation Status | 3 |
| US-03 — Delivery Partner Assignment | 3 |
| US-06 — Order Status Notifications | 3 |
| Total | 14 |

Sprint Planning Summary

During Sprint Planning, the refined Product Backlog was reviewed and four user stories were selected based on business priority, dependencies, complexity, and available sprint capacity. The selected stories total 14 story points and form a logical foundation for the Real-Time Order Tracking Enhancement. The remaining stories — Live Delivery Tracking and ETA Display — remained in the Product Backlog for a future sprint.

# 3. Daily Stand-up — Day 1

| Team Member | Yesterday | Today | Blockers |
| --- | --- | --- | --- |
| Business Analyst | Finalized user stories and acceptance criteria | Clarify requirements and support the development team | None |
| Developer | Reviewed US-01 requirements | Start development of order status functionality | None |
| QA Tester | Reviewed acceptance criteria | Prepare test scenarios for US-01 | None |
| UI/UX Designer | Reviewed tracking requirements | Design order tracking UI | None |

BA Stand-up Contribution — Day 1

Confirmed that acceptance criteria for the Sprint 1 user stories were documented and available for the development and QA teams, and remained available to clarify functional requirements and resolve implementation questions. No blockers were identified during the Day 1 stand-up.

Requirement Clarification Log

| ID | User Story | Clarification Required | BA Clarification | Decision |
| --- | --- | --- | --- | --- |
| RC-01 | US-02 | When should status change to "Ready for Pickup"? | Restaurant updates status once food preparation is completed and ready to hand over. | Status updated by restaurant via order management system. |
| RC-02 | US-01 | Which statuses should be visible to the customer? | Customer should see key order stages. | Display: Order Placed, Confirmed, Preparing, Ready for Pickup, Out for Delivery, Delivered. |
| RC-03 | US-03 | When should the assignment notification be triggered? | Notification should trigger after successful delivery partner assignment. | Send notification immediately after successful assignment. |

# 4. Sprint Review — Sprint 1

Stakeholders (simulated): Product Owner, Business Representative, Development Team, QA Representative, and Business Analyst (project owner).

Completed User Stories

| User Story | Points | Status |
| --- | --- | --- |
| US-01 — View Current Order Status | 5 | Completed |
| US-02 — Food Preparation Status | 3 | Completed |
| US-03 — Delivery Partner Assignment | 3 | Completed |
| US-06 — Order Status Notifications | 3 | Completed |
| Total | 14 | Completed |

Sprint Review Summary

Completed functionality was demonstrated against the agreed acceptance criteria, covering order status visibility, food preparation status, delivery partner assignment notifications, and order status notifications. The defect identified during testing was resolved and successfully retested before UAT. Simulated stakeholders reviewed and accepted the Sprint 1 outcome.

Stakeholder Feedback for Future Iterations

- Live delivery tracking using a map

- Estimated Time of Arrival (ETA)

- More detailed delivery progress information

Outcome

Sprint 1 successfully achieved its Sprint Goal. Additional stakeholder feedback was captured as input for future backlog prioritization.

# 5. Sprint Retrospective — Sprint 1

Conducted as a simulated Agile ceremony to identify what went well, what could be improved, and what actions to take in the next sprint.

What Went Well

- User stories were clearly defined with acceptance criteria.

- Requirements were clarified before and during development.

- Dependencies between user stories were identified during backlog refinement.

- Test cases were prepared based on business requirements.

- The identified notification defect was documented and resolved.

- UAT was completed successfully for the Sprint 1 functionality.

- Stakeholder feedback was captured during the Sprint Review.

What Could Be Improved

- Some requirements could have been clarified earlier to reduce development questions.

- Additional edge cases could have been identified during test-case preparation.

- More detailed technical dependencies could be identified during backlog refinement.

- Earlier stakeholder involvement in requirement validation could improve feedback cycles.

Action Items for Next Sprint

| Action Item | Owner | Priority |
| --- | --- | --- |
| Review edge cases before development begins | Business Analyst | High |
| Improve requirement clarification during refinement | Business Analyst + Development Team | High |
| Review technical dependencies for live tracking | BA + Development Team | Medium |
| Validate future requirements with stakeholders earlier | BA + Product Owner | High |

Retrospective Outcome

The team identified opportunities to improve requirement clarity, testing coverage, dependency analysis, and stakeholder involvement in future iterations. Identified action items will be considered during planning for the next sprint.

Note: These Agile ceremonies are simulated exercises conducted as part of a self-initiated Business Analyst portfolio project and do not represent an actual client engagement.